## Backlog
Issue Type | Id | Summary | Description | Parent | Main flow | Priority | Story Points | Sprint | Status | Assignee | Baseline
Epic | EP01 | Identity and access | Login, silent renewal, logout, password reset, platform accounts, and roles and permissions held as data with CASL policies on every mutating endpoint. |  |  |  | 8
Story | US-UC08 | UC-08 Authenticate | As an Org Manager, Org Operator, TrekLink Staff or TrekLink Admin, I want to log in, renew the session silently and log out. FR-AUTH-01: WHEN a mutating request is received, the system SHALL require both a valid JWT and a CASL policy that permits the action, and SHALL return 401 or 403 in the standard envelope otherwise. FR-AUTH-02: WHEN valid credentials are submitted, the system SHALL issue a short-lived access token and a refresh token; IF credentials are invalid, THEN the system SHALL return 401 without revealing which field was wrong. FR-AUTH-03: WHEN a valid refresh token is presented, the system SHALL issue a new access token and rotate the refresh token; IF a rotated refresh token is reused, THEN the system SHALL revoke the whole token family. FR-AUTH-04: WHEN a user logs out, the system SHALL revoke the presented refresh token immediately. FR-AUTH-08: The system SHALL record every authentication event with actor, event type, IP and UTC time, append-only, and SHALL NOT store an attempted password in any form. Alternatives and exceptions: Wrong credentials: MSG09. Reused refresh token: the token family is revoked. | EP01 | X | High | 3 | 3 | Backlog | LongLP | yes
Story | US-UC09 | UC-09 Reset Password | As an Org Manager, Org Operator, TrekLink Staff or TrekLink Admin, I want to reset a forgotten password by email OTP; Staff may trigger it without seeing it. FR-AUTH-05: WHEN a password reset is requested, the system SHALL send a single-use, time-limited code to the registered email only and SHALL respond identically for unknown emails; TrekLink Staff SHALL be able to trigger a reset and SHALL NOT be able to view or set a password. Business rules: BR-35 (SRS section 3.3). Alternatives and exceptions: Code wrong, expired or used: MSG08. Unknown email: the same response as a known one. | EP01 | X | High | 3 | 3 | Backlog | LongLP | yes
Story | US-UC10 | UC-10 Manage Platform Accounts | As a TrekLink Admin, I want to create, deactivate and assign roles to TrekLink Staff and Admin accounts. FR-AUTH-06: The system SHALL store roles and permissions as data, and a permission change SHALL take effect on the next request without a redeploy. FR-AUTH-07: WHEN an account is deactivated, the system SHALL reject its refresh tokens immediately. FR-AUTH-09: WHEN a record is deleted, the system SHALL mark it deleted and retain it, except where hard deletion is specified for that record type. FR-AUTH-10: The system SHALL grant a TrekLink Admin every permission of TrekLink Staff, and an Org Manager every permission of an Org Operator within the same organization. Alternatives and exceptions: Email already registered: MSG10. | EP01 | X | High | 2 | 3 | Backlog | LongLP | yes
Epic | EP02 | Organizations | Organization self-registration, verification with the master contract (NDA and software licence), approval, members, the on-duty roster, API keys and Field Station credentials, suspension and compliance cases. |  |  |  | 27
Story | US-UC01 | UC-01 Register Organization | As a Guest, I want to submit a company's details and its Manager's contact to open a Pending organization. FR-ORG-01: WHEN a Guest submits a registration with a tax code and a Manager email not already registered, the system SHALL create the organization in `PENDING` and its Manager account, which SHALL NOT be able to request a contract. Alternatives and exceptions: Tax code or email already registered: MSG10. Required field empty: MSG02. | EP02 | MF-01 | High | 3 | 3 | Backlog | TanNB | yes
Story | US-UC02 | UC-02 Verify Organization | As a TrekLink Staff, I want to record the in-person or phone verification, the documents seen and the signed master contract with its NDA and software licence. FR-ORG-02: WHEN TrekLink Staff record a verification, the system SHALL store the documents seen, the signed master contract and the verifying Staff member, SHALL require that the contract includes the non-disclosure agreement and the Field Station software licence, and SHALL notify Admins. Business rules: BR-43 (SRS section 3.3). Alternatives and exceptions: Documents do not match the registration: Staff record the mismatch; the organization stays `PENDING`. NDA or software licence missing from the master contract: the verification is refused and the organization stays `PENDING`. | EP02 | MF-01 | High | 3 | 3 | Backlog | TanNB | no
Story | US-UC03 | UC-03 Approve Organization | As a TrekLink Admin, I want to approve a verified organization so it becomes Active, or reject it with a reason. FR-ORG-03: WHEN an Admin approves a verified organization, the system SHALL move it to `ACTIVE`; IF it is not verified, THEN the system SHALL refuse the approval; WHEN an Admin rejects it, the system SHALL move it to `REJECTED` with the reason. Business rules: BR-01 (SRS section 3.3). Alternatives and exceptions: The Admin rejects with a reason: `REJECTED`, MSG16. Not yet verified: approval refused, MSG21. | EP02 | MF-01 | High | 3 | 3 | Backlog | TanNB | no
Story | US-UC04 | UC-04 Manage Members | As an Org Manager, I want to invite, change the role of, and deactivate the organization's own members. FR-AUTH-06: The system SHALL store roles and permissions as data, and a permission change SHALL take effect on the next request without a redeploy. FR-AUTH-07: WHEN an account is deactivated, the system SHALL reject its refresh tokens immediately. FR-AUTH-10: The system SHALL grant a TrekLink Admin every permission of TrekLink Staff, and an Org Manager every permission of an Org Operator within the same organization. FR-ORG-04: The system SHALL let an Org Manager invite members by email with the role Manager or Operator, change roles and deactivate members, SHALL keep each organization account in exactly one organization, and SHALL refuse to deactivate the last Manager. Business rules: BR-19 (SRS section 3.3). Alternatives and exceptions: Email already belongs to another organization: MSG10. Deactivating the last Manager: refused, MSG29. A deactivated member owned an open incident: the incident moves to the backup tier (D-034). | EP02 | MF-01, MF-03 | High | 5 | 3 | Backlog | TanNB | yes
Story | US-UC05 | UC-05 Manage On-duty Roster | As an Org Manager, I want to set the primary and backup on-duty members for each shift window. FR-ORG-05: The system SHALL let an Org Manager define shift windows with a primary and a backup on-duty member, and SHALL warn about any window with no primary. Business rules: BR-16 (SRS section 3.3). Alternatives and exceptions: A window without a primary: warning MSG22; alerts in that window start at the backup tier. | EP02 | MF-03 | Medium | 2 | 4 | Backlog | TanNB | no
Story | US-UC06 | UC-06 Manage API Keys and Field Station Credentials | As an Org Manager, I want to create, name and revoke the organization's read-only telemetry API keys and its Field Station credentials. FR-ORG-06: WHEN an Org Manager creates an API key, the system SHALL show it once, store only its hash, scope it read-only to the organization, and record its last use; WHEN a key is revoked, the system SHALL reject it from the next request. FR-ORG-09: WHEN an Admin suspends an organization, or Staff or an Admin revoke its Field Station credentials or API keys, from a compliance case, the system SHALL record the action on the case with its actor and UTC time. FR-EVT-14: WHEN an Org Manager creates a Field Station credential, the system SHALL show it once, store only its hash, bind it to the organization, and accept MQTT publishes under it only for devices the organization rents, or returned within the configured late-upload grace period; WHEN the Manager, TrekLink Staff or an Admin revokes it, the broker SHALL refuse it from the next connection. FR-EVT-18: The system SHALL let an Org Manager download the current Field Station release from the portal with its version shown, and the Field Station SHALL report its version in every health message; WHERE a station runs an older version, the system SHALL show it as outdated to the Manager and to TrekLink Staff. Business rules: BR-19, BR-20 (SRS section 3.3). Alternatives and exceptions: A revoked or unknown key or credential is used: 401, MSG26; the broker refuses the Field Station connection. | EP02 | MF-02, MF-04 | Medium | 3 | 3 | Backlog | TanNB | no
Story | US-UC07 | UC-07 Suspend Organization | As a TrekLink Admin, I want to suspend an organization on a defaulted contract or by decision, and reactivate it after settlement. FR-ORG-07: WHEN a contract defaults or an Admin suspends an organization, the system SHALL move it to `SUSPENDED`, refuse new contracts, and keep monitoring and alert routing for its rented devices; the system SHALL let an Admin reactivate it only when no balance is outstanding. FR-ORG-09: WHEN an Admin suspends an organization, or Staff or an Admin revoke its Field Station credentials or API keys, from a compliance case, the system SHALL record the action on the case with its actor and UTC time. Business rules: BR-26, BR-32 (SRS section 3.3). Alternatives and exceptions: Reactivation with an unpaid balance: refused, MSG25. | EP02 | MF-05 | Medium | 3 | 5 | Backlog | TanNB | no
Story | US-UC50 | UC-50 Default Overdue Contract | System story: Mark an overdue contract defaulted after the threshold and start tracking and reporting. FR-ORG-07: WHEN a contract defaults or an Admin suspends an organization, the system SHALL move it to `SUSPENDED`, refuse new contracts, and keep monitoring and alert routing for its rented devices; the system SHALL let an Admin reactivate it only when no balance is outstanding. FR-CON-12: IF a `RETURN_DUE` contract's devices are not all back by the return grace period, THEN the system SHALL move it to `OVERDUE`; IF it stays `OVERDUE` beyond the default threshold, THEN the system SHALL move it to `DEFAULTED`. Business rules: BR-26 (SRS section 3.3). No alternative flow in the SRS specification. | EP02 | MF-05 | High | 2 | 5 | Backlog | TanNB | yes
Story | US-UC63 | UC-63 Handle Compliance Case | As a TrekLink Staff or TrekLink Admin, I want to record a suspected fraud, theft, IP violation or NDA breach by an organization, and the actions taken. FR-ORG-08: WHEN TrekLink Staff or an Admin open a compliance case against an organization, the system SHALL record its type (suspected fraud, suspected theft, IP violation, NDA breach or other breach), evidence notes and linked loss cases or contracts; IF the type is suspected fraud or suspected theft, THEN the system SHALL refuse to close it without a police report reference. FR-ORG-09: WHEN an Admin suspends an organization, or Staff or an Admin revoke its Field Station credentials or API keys, from a compliance case, the system SHALL record the action on the case with its actor and UTC time. Business rules: BR-40 (SRS section 3.3). Alternatives and exceptions: A suspected fraud or theft case without a police report reference: closing is refused. | EP02 | MF-05 | Low | 3 | 5 | Backlog | TanNB | no
Epic | EP03 | Device assets and maintenance | The device lifecycle: registration, intake check, hardware variants with service plans, provisioning, inspection, loss cases, disposal, maintenance with cost approval, the weekly service scan and stock-take. |  |  |  | 40
Story | US-UC11 | UC-11 Register Device | As a TrekLink Staff, I want to record a new unit's asset tag, radio identity, hardware variant and firmware version. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-DEV-02: WHEN Staff register a device, the system SHALL require an asset tag and a `nodeNum` unique across all devices ever registered, a hardware variant and a firmware version, and SHALL create it in `IN_INTAKE`. Business rules: BR-10 (SRS section 3.3). Alternatives and exceptions: Asset tag or `nodeNum` already registered, including retired units: MSG10. | EP03 | MF-01 | High | 3 | 3 | Backlog | Khoa | yes
Story | US-UC12 | UC-12 Pass Intake Check | As a TrekLink Staff, I want to run the intake quality check so a new or repaired unit becomes Available. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-DEV-03: WHEN Staff record an intake check, the system SHALL require a result for GPS fix, radio, battery and, where the variant has one, the motion sensor, and SHALL move the device to `AVAILABLE` on a pass or `MAINTENANCE` on a failure. FR-DEV-17: WHEN a device first passes the intake check, the system SHALL set its service due date from its variant's service interval, and WHEN a `SCHEDULED` record is completed, SHALL move that date forward by the interval; other maintenance SHALL NOT change it. Business rules: BR-10 (SRS section 3.3). Alternatives and exceptions: A failed check: the device goes to `MAINTENANCE` with the failed item. | EP03 | MF-01 | High | 2 | 3 | Backlog | Khoa | no
Story | US-UC13 | UC-13 Manage Hardware Variants | As a TrekLink Admin, I want to maintain the hardware variants, their specifications, remaining-value schedule and service plan. FR-DEV-04: The system SHALL let an Admin maintain hardware variants with a remaining-value schedule, a service interval in days and a service checklist, and SHALL refuse to delete a variant that has registered devices. Alternatives and exceptions: Deleting a variant with registered devices: refused, MSG29. | EP03 | X | High | 2 | 3 | Backlog | Khoa | yes
Story | US-UC14 | UC-14 Provision Device | As a TrekLink Staff, I want to write the organization's channel key to a device at handover; only the key version is stored. FR-DEV-05: WHEN a device is provisioned, the system SHALL record the organization's channel key version and time, and SHALL never store, display, return or log the key. Business rules: BR-09 (SRS section 3.3). Alternatives and exceptions: Write fails: the device goes to `MAINTENANCE` and Staff swap in another unit (E01-5). | EP03 | MF-01 | High | 2 | 3 | Backlog | Khoa | yes
Story | US-UC43 | UC-43 Check In Device | As a TrekLink Staff, I want to receive a returned device at the counter by asset tag; it becomes Returned. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-MON-08: WHEN a device is checked in, the system SHALL stop delivering to the renting organization any of its data whose occurrence time is after the check-in, and SHALL keep delivering late events attributed to that organization's custody interval. Business rules: BR-27 (SRS section 3.3). Alternatives and exceptions: A tag from another contract: MSG12. Device returned while still due for a term: the term stays payable. | EP03 | MF-05 | High | 3 | 5 | Backlog | Khoa | yes
Story | US-UC44 | UC-44 Reset and Inspect Device | As a TrekLink Staff, I want to wipe the renter's key and data from a returned device and record its condition. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-DEV-07: WHEN a device is checked in, the system SHALL require a logged reset (channel key removed, node database and owner name cleared) before the device can move to `AVAILABLE`. FR-DEV-19: WHEN an inspection of a returned device passes and the device is due for service or its firmware differs from its variant's baseline, the system SHALL move it to `MAINTENANCE` with a `SCHEDULED` or `FIRMWARE_UPDATE` record instead of `AVAILABLE`. Business rules: BR-24, BR-28 (SRS section 3.3). Alternatives and exceptions: Reset fails: the device goes to `MAINTENANCE` and cannot be `AVAILABLE` until it succeeds. | EP03 | MF-05 | High | 3 | 5 | Backlog | Khoa | yes
Story | US-UC49 | UC-49 Report Lost Device | As an Org Manager or TrekLink Staff, I want to report a device in service as lost, which opens a loss case. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-DEV-12: WHEN an Org Manager reports one of its rented devices lost, or TrekLink Staff report any device in service lost, the system SHALL move the device to `LOST` and open one loss case in `REPORTED`, recording the reporter, the time and the device's last seen time and position; IF a loss case is already open for the device, THEN the system SHALL refuse. Business rules: BR-37 (SRS section 3.3). Alternatives and exceptions: A loss case is already open for the device: refused, the open case is shown. | EP03 | MF-05 | High | 3 | 5 | Backlog | Khoa | yes
Story | US-UC52 | UC-52 Record Maintenance | As a TrekLink Staff, I want to open, cost and complete a maintenance record for a faulty unit, a unit due for service or a firmware update. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-DEV-08: WHEN Staff move a device to `MAINTENANCE`, the system SHALL require a reason and an expected completion date, and SHALL keep the device unallocatable until it passes the intake check again. FR-DEV-17: WHEN a device first passes the intake check, the system SHALL set its service due date from its variant's service interval, and WHEN a `SCHEDULED` record is completed, SHALL move that date forward by the interval; other maintenance SHALL NOT change it. FR-DEV-20: WHEN Staff record a maintenance estimate above `devices.maintenanceApprovalThresholdVnd`, or an actual cost above the approved amount, the system SHALL set the record `PENDING_APPROVAL` and refuse to complete it until an Admin other than the person who recorded the estimate approves an amount or rejects it with a reason. FR-DEV-21: WHEN Staff complete a maintenance record, the system SHALL require the work done, the actual cost, whether it was in-house or by a named vendor, a result for each checklist item of a `SCHEDULED` record and a new firmware version for a `FIRMWARE_UPDATE` record, and SHALL update the device's firmware version when one is given. Business rules: BR-10, BR-44, BR-45 (SRS section 3.3). Alternatives and exceptions: Estimate above the approval threshold: the record waits for an Admin (UC-64) before it can be completed. Actual cost above the approved amount: the record goes back for approval. Beyond repair: Staff close the record `UNREPAIRABLE` and an Admin retires the device (UC-53). | EP03 | MF-05 | High | 5 | 5 | Backlog | Khoa | yes
Story | US-UC53 | UC-53 Retire Device | As a TrekLink Admin, I want to retire a device beyond repair, keeping its history; a settled loss retires its device through the loss case. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-DEV-09: WHEN an Admin retires a device, the system SHALL set `RETIRED` without deleting the device or its history, and SHALL refuse while the device is on a running contract. FR-DEV-11: The system SHALL present a read-only chronological history per device of contracts, incidents, inspections, maintenance and state changes, each with actor and UTC time. Business rules: BR-10 (SRS section 3.3). Alternatives and exceptions: Device on a running contract: refused, MSG29. | EP03 | MF-05 | High | 2 | 5 | Backlog | Khoa | yes
Story | US-UC54 | UC-54 Run Stock-take | As a TrekLink Staff, I want to reconcile the register with units counted in stock and units seen recently in the field. FR-DEV-10: The system SHALL produce a stock-take that lists in-stock units by asset tag, marks rented units seen within the confirmation threshold, and lists every unit confirmed by neither, from which Staff may report a loss. No alternative flow in the SRS specification. | EP03 | MF-05 | Low | 2 | 5 | Backlog | Khoa | no
Story | US-UC60 | UC-60 Resolve Loss Case | As a TrekLink Staff or TrekLink Admin, I want to triage a loss case, record its custody and key exposure, then close it as recovered or settle the confirmed loss. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-DEV-13: WHEN Staff triage a loss case, the system SHALL record the custody, the organization whose custody interval contains the last seen time or TrekLink, SHALL move the case to `SEARCHING`, and for renter custody SHALL mark the organization's channel key exposed and notify its Manager; IF the case is flagged as suspected theft or fraud, THEN the system SHALL open or link a compliance case. FR-DEV-14: WHEN a lost device is brought back to the counter, the system SHALL move its loss case to `RECOVERED` and the device to `RETURNED`, so that it is reset and inspected before it can be `AVAILABLE`. FR-DEV-15: WHEN Staff confirm a loss, or the search window `devices.lossSearchDays` elapses while the case is `SEARCHING`, the system SHALL move the case to `CONFIRMED`; WHEN its charge is applied, reduced, waived or written off, the system SHALL move the case to `SETTLED` and the device to `RETIRED`. FR-BILL-05: WHEN a loss case is confirmed and the device was in renter custody, the system SHALL charge its remaining value from the variant's schedule to that contract; a loss in TrekLink custody SHALL be written off with no charge. FR-BILL-11: WHEN an Admin who did not triage a loss case reduces or waives its charge, the system SHALL require a reason and record the decision; the system SHALL refuse the Staff member who triaged the case. Business rules: BR-25, BR-38, BR-39 (SRS section 3.3). Alternatives and exceptions: Signs of theft or fraud: Staff flag the case; a compliance case is opened or linked (UC-63). The device turns up after settlement: it is recovered to `RETURNED`; the charge stands unless an Admin records an adjustment. | EP03 | MF-05 | Medium | 5 | 5 | Backlog | Khoa | no
Story | US-UC62 | UC-62 Dispose Device | As a TrekLink Admin, I want to dispose of a retired device after a verified wipe, keeping its history. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-DEV-16: WHEN an Admin disposes of a retired device, the system SHALL require a recorded wipe of the channel key, node database and owner name, SHALL move the device to `DISPOSED`, and SHALL keep the device and its history. Business rules: BR-42 (SRS section 3.3). Alternatives and exceptions: No recorded wipe: refused. | EP03 | MF-05 | Low | 2 | 5 | Backlog | Khoa | no
Story | US-UC64 | UC-64 Approve Maintenance Cost | As a TrekLink Admin, I want to approve or reject a maintenance estimate above the threshold; the approver never recorded the estimate. FR-DEV-20: WHEN Staff record a maintenance estimate above `devices.maintenanceApprovalThresholdVnd`, or an actual cost above the approved amount, the system SHALL set the record `PENDING_APPROVAL` and refuse to complete it until an Admin other than the person who recorded the estimate approves an amount or rejects it with a reason. Business rules: BR-44 (SRS section 3.3). Alternatives and exceptions: The Admin rejects with a reason: the record returns to `OPEN` to be re-estimated or closed `UNREPAIRABLE`. The Admin recorded the estimate: refused, MSG29. | EP03 | MF-05 | Low | 3 | 5 | Backlog | Khoa | no
Story | US-UC65 | UC-65 Scan for Due Service | System story: Each week open service and firmware records for available units that fall due, and list them for Staff. FR-DEV-18: The system SHALL run a weekly scan that selects every device whose service falls due before the next run plus `devices.maintenanceLeadDays`, or whose firmware version differs from its variant's baseline, SHALL open a `SCHEDULED` or `FIRMWARE_UPDATE` record for each such `AVAILABLE` device without an open record and move it to `MAINTENANCE`, and SHALL send TrekLink Staff the list. Business rules: BR-45 (SRS section 3.3). Alternatives and exceptions: A due unit is `RESERVED` or `RENTED`: it stays on its contract and is routed to `MAINTENANCE` when its inspection passes after check-in (UC-44). A unit already has an open record: no second record. | EP03 | MF-05 | Low | 3 | 5 | Backlog | Khoa | no
Epic | EP04 | Rental contracts | Rental contract request, availability check, approval, handover with signed note, cancellation notice, monthly roll-over, holder labels, mid-contract replacement and closure. |  |  |  | 35
Story | US-UC15 | UC-15 Request Rental Contract | As an Org Manager, I want to ask for a monthly or day plan with a hardware variant, a quantity and a start date. FR-CON-01: WHEN an Org Manager requests a contract, the system SHALL require a plan (monthly, or a day plan of a configured length), a hardware variant, a quantity and a start date, SHALL reject a quantity below the minimum order quantity, and SHALL create the contract in `REQUESTED`. FR-CON-02: IF the requesting organization is not `ACTIVE`, THEN the system SHALL reject the request. FR-CON-07: The system SHALL reject any change to a running contract's plan, variant or quantity. FR-BILL-01: The system SHALL price a monthly term as the variant's monthly price times the quantity, with a holding fee of the configured ratio (default one half) due at the term start, retained as part of the fee, and the remainder due at the term end. FR-BILL-02: The system SHALL price a day plan as the variant's monthly price divided by 30, times the configured premium of at least 1, times the plan length and the quantity, due in full before handover. Business rules: BR-01, BR-02, BR-06, BR-07 (SRS section 3.3). Alternatives and exceptions: Below the minimum order quantity: MSG13 (E01-2). Not enough devices: MSG11. Organization not `ACTIVE`: MSG26 (E01-3). | EP04 | MF-01 | High | 5 | 3 | Backlog | LongLP | yes
Story | US-UC16 | UC-16 Verify Device Availability | System story: Check that enough Available units of the variant exist for the requested quantity. FR-CON-03: WHEN Staff approve a contract, the system SHALL, in one transaction holding row locks on the devices, reserve exactly the requested number of `AVAILABLE` devices of the variant, and SHALL refuse the approval if fewer are available. Business rules: BR-03 (SRS section 3.3). No alternative flow in the SRS specification. | EP04 | MF-01 | High | 2 | 3 | Backlog | LongLP | yes
Story | US-UC17 | UC-17 Approve Rental Contract | As a TrekLink Staff, I want to approve a requested contract, reserving specific devices, or reject it with a reason. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-CON-03: WHEN Staff approve a contract, the system SHALL, in one transaction holding row locks on the devices, reserve exactly the requested number of `AVAILABLE` devices of the variant, and SHALL refuse the approval if fewer are available. FR-CON-11: The system SHALL allocate to a new contract only devices in `AVAILABLE`, so that a device passes from one contract to another only through check-in, reset and inspection. Business rules: BR-03, BR-04 (SRS section 3.3). Alternatives and exceptions: Another approval took the last devices: refused, MSG11 (E01-1). Staff reject with a reason: `REJECTED`, MSG16. | EP04 | MF-01 | High | 3 | 3 | Backlog | LongLP | yes
Story | US-UC18 | UC-18 Cancel Rental Contract | As an Org Manager or TrekLink Staff, I want to cancel a contract before handover; reserved devices return to Available. FR-CON-04: IF an approved contract is not handed over within the configured reservation expiry, THEN the system SHALL notify Staff and the Org Manager; WHEN Staff or the Manager cancel a contract before handover, the system SHALL release its devices to `AVAILABLE`. Business rules: BR-05 (SRS section 3.3). Alternatives and exceptions: A first payment was already made: retained per the cancellation rule, MSG15. Contract already `ACTIVE`: refused; the monthly path is notice (UC-23), MSG28. | EP04 | MF-01 | High | 3 | 3 | Backlog | LongLP | yes
Story | US-UC20 | UC-20 Hand Over Devices | As a TrekLink Staff, I want to hand provisioned devices and the Field Station package to the organization at the counter. FR-DEV-01: The system SHALL change device state only through the device lifecycle of D-035 and D-045, SHALL reject any other change with 409, and SHALL write an append-only audit row for each transition. FR-CON-05: WHEN a handover is completed, the system SHALL require the first payment recorded, the Manager's identity verified, every device provisioned and checked, and the signed handover note, and SHALL then move the contract to `ACTIVE` and its devices to `RENTED` in one transaction. FR-BILL-02: The system SHALL price a day plan as the variant's monthly price divided by 30, times the configured premium of at least 1, times the plan length and the quantity, due in full before handover. Business rules: BR-09, BR-10 (SRS section 3.3). Alternatives and exceptions: First payment not recorded: refused, MSG23 (E01-4). A device fails its check: swapped for another `AVAILABLE` unit of the variant; if none, the handover is held (E01-5). | EP04 | MF-01 | High | 5 | 3 | Backlog | LongLP | yes
Story | US-UC21 | UC-21 Sign Handover Note | System story: Capture the Manager's signature on the handover note listing every device by asset tag. FR-CON-05: WHEN a handover is completed, the system SHALL require the first payment recorded, the Manager's identity verified, every device provisioned and checked, and the signed handover note, and SHALL then move the contract to `ACTIVE` and its devices to `RENTED` in one transaction. FR-CON-06: The system SHALL generate the handover note listing the organization, plan, term dates and every device by asset tag, SHALL stamp the signature into it and store its hash, and SHALL never alter it afterwards. Business rules: BR-09 (SRS section 3.3). No alternative flow in the SRS specification. | EP04 | MF-01 | High | 2 | 3 | Backlog | LongLP | yes
Story | US-UC23 | UC-23 Give Cancellation Notice | As an Org Manager, I want to give notice during a running monthly term so the contract ends at that term's end. FR-CON-09: WHEN an Org Manager gives notice on a running monthly contract, the system SHALL move it to `ENDING` effective at the current term's end; IF the contract is a day plan, THEN the system SHALL refuse the notice. Business rules: BR-08 (SRS section 3.3). Alternatives and exceptions: Day plan: refused, it ends by itself, MSG28. | EP04 | MF-05 | High | 2 | 5 | Backlog | LongLP | no
Story | US-UC24 | UC-24 Roll Over Monthly Term | System story: At a term boundary, close the term and open the next one, or end the contract after notice. FR-CON-08: WHEN a monthly term ends without notice, the system SHALL close the term, make its balance due and open the next term with its holding fee due; WHEN it ends after notice, the system SHALL move the contract to `RETURN_DUE`. FR-CON-10: WHEN a day plan reaches its end date, the system SHALL move the contract to `RETURN_DUE`, and SHALL offer no extension. FR-BILL-01: The system SHALL price a monthly term as the variant's monthly price times the quantity, with a holding fee of the configured ratio (default one half) due at the term start, retained as part of the fee, and the remainder due at the term end. Business rules: BR-06, BR-08 (SRS section 3.3). Alternatives and exceptions: Previous balance unpaid at the boundary: the contract continues and the amounts accumulate; overdue rules apply to payments. | EP04 | MF-05 | High | 3 | 5 | Backlog | LongLP | no
Story | US-UC25 | UC-25 Label Device Holder | As an Org Manager or Org Operator, I want to optionally attach the carrier's name, phone and emergency contact to a rented device. FR-CON-14: WHERE an organization labels a rented device with its holder's name, phone and emergency contact, the system SHALL show the label on the map and in that device's alerts, and SHALL erase it when the contract closes. Business rules: BR-33 (SRS section 3.3). No alternative flow in the SRS specification. | EP04 | MF-03, MF-04 | High | 2 | 4 | Backlog | LongLP | yes
Story | US-UC51 | UC-51 Close Rental Contract | As a TrekLink Staff, I want to close a contract once every device is back or recorded lost, everything is paid and no incident is open. FR-CON-13: WHEN Staff close a contract, the system SHALL require every device checked in, or lost with its loss case `SETTLED`, no outstanding balance, and no incident on its devices outside `CLOSED`; otherwise it SHALL refuse. FR-CON-14: WHERE an organization labels a rented device with its holder's name, phone and emergency contact, the system SHALL show the label on the map and in that device's alerts, and SHALL erase it when the contract closes. Business rules: BR-27, BR-33 (SRS section 3.3). Alternatives and exceptions: Balance outstanding: refused, MSG25 (E05-4). An incident still open: refused, MSG29 (E05-7). | EP04 | MF-05 | High | 3 | 5 | Backlog | LongLP | no
Story | US-UC55 | UC-55 View Contracts and Invoices | As an Org Manager, I want to see the organization's contracts, terms, invoices, payments and handover notes. FR-AUTH-11: WHILE an organization member or an organization API key is authenticated, the system SHALL restrict every read and push of devices, positions, telemetry, incidents, contracts and invoices, over REST and WebSocket, to that organization's records, and SHALL enforce this on the server. FR-CON-07: The system SHALL reject any change to a running contract's plan, variant or quantity. Business rules: BR-19 (SRS section 3.3). No alternative flow in the SRS specification. | EP04 | MF-01, MF-05 | High | 2 | 3 | Backlog | LongNN | yes
Story | US-UC61 | UC-61 Replace Device on Contract | As a TrekLink Staff, I want to replace a faulty or lost unit on a running contract with an available unit of the same variant. FR-CON-15: WHEN Staff replace a faulty device, or a device with an open loss case, on an `ACTIVE` or `ENDING` contract, the system SHALL allocate an `AVAILABLE` device of the same variant, require it provisioned and the replacement signed by the Manager, open its own custody interval, check in the faulty device if present, and keep the contract's plan, variant and quantity unchanged. Business rules: BR-41 (SRS section 3.3). Alternatives and exceptions: No `AVAILABLE` unit of the variant: the replacement is refused and the contract continues one unit short. Organization `SUSPENDED`: refused. | EP04 | MF-05 | Medium | 3 | 5 | Backlog | LongLP | no
Epic | EP05 | Field data and synchronization | Ingestion of field events from the Field Station with idempotency, the offline queue flush in priority order, the local field picture and the Field Station release download. |  |  |  | 13
Story | US-UC26 | UC-26 Ingest Field Event | System story: Decode, deduplicate, persist and route one field event from the mesh. FR-DEV-06: WHEN a telemetry or position event is ingested, the system SHALL update the device's battery, last-seen time and last position, and SHALL discard a reading older than the stored last-seen time. FR-EVT-01: WHEN a field event is ingested, the system SHALL derive `eventId = sha256(nodeNum : packetId)`, insert it under a database unique index inside the same transaction as its side effects, and treat a repeated `eventId` as a no-op. FR-EVT-02: WHEN the Field Station parses a mesh event, it SHALL classify it P0 (SOS), P1 (incident location), P2 (GPS) or P3 (telemetry) and persist it to its local queue before any network attempt. FR-EVT-05: IF a payload cannot be decoded, THEN the system SHALL log it raw, count it, drop it and continue without blocking the queue head. FR-EVT-08: The system SHALL order events by queue sequence and priority, never by wall-clock comparison across hosts, and SHALL treat a device `rx_time` of 0 as unknown. FR-EVT-09: WHEN a text event is decoded, the system SHALL test the `SOS - FALL DETECTED` prefix before the `SOS - ` prefix and SHALL classify both as SOS. FR-EVT-10: The system SHALL accept events from the stock Meshtastic MQTT JSON topic `<root>/2/json/...` through an ingress adapter that produces one canonical event envelope; the protobuf topic `<root>/2/e/...` stays permitted by the broker and is not ingested. FR-EVT-11: The system SHALL write one append-only synchronization audit row per ingestion attempt, recording acceptance or duplicate rejection. FR-EVT-14: WHEN an Org Manager creates a Field Station credential, the system SHALL show it once, store only its hash, bind it to the organization, and accept MQTT publishes under it only for devices the organization rents, or returned within the configured late-upload grace period; WHEN the Manager, TrekLink Staff or an Admin revokes it, the broker SHALL refuse it from the next connection. FR-EVT-15: WHEN a field event is ingested, the system SHALL record its server receipt time and SHALL derive its occurrence time, recording the source used: the Field Station's capture time corrected by the clock offset the station reports at each sync; otherwise the device `rx_time` when it is non-zero and within the configured plausibility window before receipt; otherwise the receipt time. Occurrence time SHALL be used for attribution only, never for ordering events across hosts. FR-EVT-16: WHEN an event's occurrence time is derived, the system SHALL attribute the event to the device's custody interval, from handover to check-in or loss, that contains that time, and SHALL accept the attribution only when the uploading Field Station's organization is the interval's organization. FR-EVT-17: IF no custody interval contains an event's occurrence time, the uploading organization differs from the interval's organization, or the occurrence time lies within the configured margin of a handover or check-in, THEN the system SHALL mark the event `UNATTRIBUTED`, SHALL make it visible to TrekLink Staff and Admin only and SHALL deliver it to no organization. FR-MON-04: IF a position lies outside the configured bounds or implies an implausible jump, THEN the system SHALL reject it, log it and not plot it. Business rules: BR-11, BR-36 (SRS section 3.3). Alternatives and exceptions: Duplicate `eventId`: no-op, audited (E02-2). Undecodable payload: logged, counted, dropped (E02-4). Late event from a device since returned and rented again: attributed to the earlier custody interval (E02-7). No custody interval matches, or the time is too close to a handover: `UNATTRIBUTED`, Staff only (E02-8). | EP05 | MF-02 | High | 8 | 3 | Backlog | Khoa | yes
Story | US-UC27 | UC-27 Flush Offline Queue | System story: Upload the events queued during an outage, highest priority first, once the uplink returns. FR-EVT-02: WHEN the Field Station parses a mesh event, it SHALL classify it P0 (SOS), P1 (incident location), P2 (GPS) or P3 (telemetry) and persist it to its local queue before any network attempt. FR-EVT-03: WHEN the uplink is restored, the Field Station SHALL flush queued events ordered by priority tier and then by queue sequence, so that every P0 event is sent before any P1, P2 or P3 event. FR-EVT-04: The Field Station SHALL mark a queued event flushed only after the broker acknowledges it; IF the uplink drops mid-flush, THEN unacknowledged events SHALL stay queued and the flush SHALL resume from the queue head. FR-EVT-06: WHILE the Field Station queue is at its configured bound, it SHALL shed P3 events first and SHALL never shed P0, logging every shed event. FR-EVT-07: WHEN the Field Station restarts with a non-empty queue, it SHALL retain every queued event and SHALL NOT mint a new `eventId` for any of them. FR-EVT-08: The system SHALL order events by queue sequence and priority, never by wall-clock comparison across hosts, and SHALL treat a device `rx_time` of 0 as unknown. Business rules: BR-12 (SRS section 3.3). Alternatives and exceptions: Uplink drops mid-flush: unacknowledged events stay queued (E02-1). Queue at its bound during a long outage: P3 shed first, never P0 (E02-5). | EP05 | MF-02 | High | 3 | 3 | Backlog | Khoa | yes
Story | US-UC28 | UC-28 View Local Field Picture | As an Org Operator, I want to see the local mesh's devices, positions and SOS on the Field Station's local page, offline too. FR-EVT-12: The Field Station SHALL serve a local page that shows the nodes heard on its mesh, their positions, battery and SOS state, its queue depth per tier and its uplink state, without internet access. Alternatives and exceptions: No node on the serial port: the page says so and how to reconnect it. | EP05 | MF-02, MF-04 | Medium | 2 | 3 | Backlog | Khoa | no
Epic | EP06 | Incidents and alerts | Incident creation from SOS and cadence anomalies, tiered alerts and escalation, acknowledgement, status reports, false alarms, reports to authorities, reopening and closing. |  |  |  | 23
Story | US-UC29 | UC-29 Create Incident | System story: Open one incident for an SOS, a fall or a suspected episode and route it to the organization. FR-EVT-09: WHEN a text event is decoded, the system SHALL test the `SOS - FALL DETECTED` prefix before the `SOS - ` prefix and SHALL classify both as SOS. FR-EVT-17: IF no custody interval contains an event's occurrence time, the uploading organization differs from the interval's organization, or the occurrence time lies within the configured margin of a handover or check-in, THEN the system SHALL mark the event `UNATTRIBUTED`, SHALL make it visible to TrekLink Staff and Admin only and SHALL deliver it to no organization. FR-INC-01: WHEN an SOS event arrives for a device with an open incident inside the correlation window, the system SHALL append it to that incident; otherwise the system SHALL create exactly one new incident. FR-INC-02: WHEN a device's position events reach the configured count N within window W, the system SHALL raise a suspected incident at lower confidence, and WHEN a late SOS text frame matches it, SHALL upgrade it to confirmed in place. FR-INC-03: WHEN an incident is created, the system SHALL, in the same transaction, route it to the contract its triggering event is attributed to, in whatever state that contract now is, and move it to `NOTIFY_PRIMARY`, or to `UNROUTED` when the event is `UNATTRIBUTED` or the contract's organization has no reachable member; the device's current holder SHALL NOT be used for routing. FR-INC-13: WHEN a device goes silent during an open incident, the system SHALL keep the incident's state, flag it stale with the last position and notify the owner. Business rules: BR-13, BR-14, BR-15, BR-36 (SRS section 3.3). Alternatives and exceptions: The SOS text frame is lost: a suspected incident from beacon cadence, lower confidence (E03-1). Contract overdue or organization suspended: still routed (E03-9). | EP06 | MF-03 | High | 5 | 4 | Backlog | HoangTK | yes
Story | US-UC30 | UC-30 Send Alert | System story: Deliver an incident alert to the current tier by web, WebSocket, email and API event. FR-INC-12: WHEN an incident changes state, the system SHALL write the alert to an outbox in the same transaction and deliver it after commit by web, WebSocket, email and API event within 2 seconds under normal load, retrying failed deliveries without blocking the state machine. Business rules: BR-16 (SRS section 3.3). Alternatives and exceptions: Delivery fails: retried and logged; the incident's timers continue (E03-7). | EP06 | MF-03 | High | 2 | 4 | Backlog | HoangTK | yes
Story | US-UC31 | UC-31 Escalate Alert Tier | System story: Move an unacknowledged incident to the next tier, and to TrekLink after the Manager tier. FR-INC-04: The system SHALL change incident state only through the transition table of D-034; each transition SHALL be one transaction with a compare-and-set on state and version and one append-only audit row with actor or `SYSTEM`, from, to, reason and UTC time. FR-INC-05: IF an alert tier is not acknowledged within its configured timeout, THEN the system SHALL move the incident to the next tier and alert it, skipping a tier with nobody rostered, and SHALL move it to `ESCALATED` after the Manager tier; a timeout job SHALL do nothing when the incident has already moved. Business rules: BR-15, BR-16 (SRS section 3.3). Alternatives and exceptions: The incident moved on meanwhile: the job does nothing. A tier has nobody rostered: it is skipped. | EP06 | MF-03 | High | 3 | 4 | Backlog | HoangTK | yes
Story | US-UC32 | UC-32 Acknowledge Incident | As an Org Operator or Org Manager, I want to take ownership of an incident's response in a single step. FR-INC-04: The system SHALL change incident state only through the transition table of D-034; each transition SHALL be one transaction with a compare-and-set on state and version and one append-only audit row with actor or `SYSTEM`, from, to, reason and UTC time. FR-INC-06: WHEN an organization member acknowledges an incident in a `NOTIFY_*`, `ESCALATED` or `REPORTED` state, the system SHALL move it to `ACKNOWLEDGED`, record the member as owner and use that time for time-to-acknowledge; a concurrent second acknowledgement SHALL be shown the owner. Business rules: BR-15 (SRS section 3.3). Alternatives and exceptions: Someone else acknowledged first: MSG27 (E03-3). | EP06 | MF-03 | High | 2 | 4 | Backlog | HoangTK | yes
Story | US-UC33 | UC-33 Report Incident Status | As an Org Operator or Org Manager, I want to report that a response is under way, give status updates, then report the outcome. FR-INC-04: The system SHALL change incident state only through the transition table of D-034; each transition SHALL be one transaction with a compare-and-set on state and version and one append-only audit row with actor or `SYSTEM`, from, to, reason and UTC time. FR-INC-07: WHILE an incident is `ACKNOWLEDGED` or `RESPONDING`, IF no status update arrives within the stale limit, THEN the system SHALL move it to `ESCALATED`, keep the owner and notify the Manager. FR-INC-08: WHEN the owner reports the outcome with a note, the system SHALL move the incident to `RESOLVED` and use that time for time-to-resolve; WHEN a member declares a false alarm with a reason, the system SHALL move it to `FALSE_ALARM`. Business rules: BR-15, BR-18 (SRS section 3.3). Alternatives and exceptions: No update within the stale limit: `ESCALATED`, owner kept, Manager notified (E03-5). An illegal transition: MSG28. | EP06 | MF-03 | High | 3 | 4 | Backlog | HoangTK | yes
Story | US-UC34 | UC-34 Declare False Alarm | As an Org Operator, Org Manager or TrekLink Staff, I want to mark an incident false with a reason; Staff do so only for an unrouted incident. FR-INC-04: The system SHALL change incident state only through the transition table of D-034; each transition SHALL be one transaction with a compare-and-set on state and version and one append-only audit row with actor or `SYSTEM`, from, to, reason and UTC time. FR-INC-08: WHEN the owner reports the outcome with a note, the system SHALL move the incident to `RESOLVED` and use that time for time-to-resolve; WHEN a member declares a false alarm with a reason, the system SHALL move it to `FALSE_ALARM`. Business rules: BR-15 (SRS section 3.3). Alternatives and exceptions: A cancel pressed on the device changes nothing: only a person declares a false alarm (D-038). | EP06 | MF-03 | High | 2 | 4 | Backlog | HoangTK | yes
Story | US-UC35 | UC-35 Report to Authorities | As a TrekLink Staff, I want to record a report to the authorities for an escalated or unrouted incident, or a defaulted contract. FR-INC-04: The system SHALL change incident state only through the transition table of D-034; each transition SHALL be one transaction with a compare-and-set on state and version and one append-only audit row with actor or `SYSTEM`, from, to, reason and UTC time. FR-INC-10: WHEN TrekLink Staff record an authority report on an `ESCALATED` or `UNROUTED` incident, the system SHALL require the agency, reference and time and SHALL move the incident to `REPORTED`. Business rules: BR-17 (SRS section 3.3). Alternatives and exceptions: The organization acknowledges later: the incident moves to `ACKNOWLEDGED`; the report stays recorded. | EP06 | MF-03, MF-05 | Medium | 2 | 4 | Backlog | HoangTK | no
Story | US-UC36 | UC-36 Reopen Incident | System story: Reopen a resolved or false-alarm incident when the same device raises a new SOS in the window. FR-INC-04: The system SHALL change incident state only through the transition table of D-034; each transition SHALL be one transaction with a compare-and-set on state and version and one append-only audit row with actor or `SYSTEM`, from, to, reason and UTC time. FR-INC-11: WHEN a new SOS episode from the same device arrives within the reopen window after `RESOLVED` or `FALSE_ALARM`, the system SHALL move the incident to `NOTIFY_PRIMARY` and increase its reopen count; WHEN the window elapses, the system SHALL move it to `CLOSED`. Business rules: BR-13, BR-15 (SRS section 3.3). Alternatives and exceptions: The window has elapsed: a new incident is created instead. | EP06 | MF-03 | High | 2 | 4 | Backlog | HoangTK | yes
Story | US-UC37 | UC-37 Close Incident | As a TrekLink Staff, I want to close an incident when its reopen window ends, or when Staff record the authority case closed. FR-INC-04: The system SHALL change incident state only through the transition table of D-034; each transition SHALL be one transaction with a compare-and-set on state and version and one append-only audit row with actor or `SYSTEM`, from, to, reason and UTC time. FR-INC-11: WHEN a new SOS episode from the same device arrives within the reopen window after `RESOLVED` or `FALSE_ALARM`, the system SHALL move the incident to `NOTIFY_PRIMARY` and increase its reopen count; WHEN the window elapses, the system SHALL move it to `CLOSED`. Business rules: BR-15 (SRS section 3.3). No alternative flow in the SRS specification. | EP06 | MF-03 | Medium | 2 | 4 | Backlog | HoangTK | no
Epic | EP07 | Live monitoring | The live map over WebSocket, the organization telemetry API, device history, stale-device marking, system health and check-in telemetry. |  |  |  | 14
Story | US-UC38 | UC-38 View Live Map | As an Org Operator, Org Manager, TrekLink Staff or TrekLink Admin, I want to see rented devices, their state and open incidents on the live map, scoped by organization. FR-AUTH-11: WHILE an organization member or an organization API key is authenticated, the system SHALL restrict every read and push of devices, positions, telemetry, incidents, contracts and invoices, over REST and WebSocket, to that organization's records, and SHALL enforce this on the server. FR-MON-01: The system SHALL render the live map with Leaflet over the configured OpenStreetMap tiles, with the Vietnamese sovereignty overlay and markers styled by device state. FR-MON-02: The system SHALL deliver live position, telemetry and incident updates over one authenticated WebSocket per client, subscribed on the server only to events attributed to the caller's organization, or to the whole fleet, including `UNATTRIBUTED` events, for TrekLink Staff and Admin. FR-MON-03: WHILE a device or Field Station has been silent beyond its configured threshold, the system SHALL display it as stale with its last-seen time. FR-MON-04: IF a position lies outside the configured bounds or implies an implausible jump, THEN the system SHALL reject it, log it and not plot it. FR-MON-05: WHEN a WebSocket client reconnects with a last-event cursor, the system SHALL replay the events after it before resuming the live stream, and the web client SHALL show a reconnecting indicator meanwhile. FR-MON-09: IF the map provider is unreachable, THEN the system SHALL show a map error state and keep the device and incident panels working. FR-CFG-03: The system SHALL hold the map provider, tile URL and default viewport in configuration. Business rules: BR-19, BR-21, BR-30 (SRS section 3.3). Alternatives and exceptions: Device silent: shown stale (E04-1). Connection lost: reconnecting indicator, resync (E04-3). Map tiles unavailable: map error, lists still live. | EP07 | MF-04 | High | 3 | 4 | Backlog | LongNN | yes
Story | US-UC39 | UC-39 Stream Telemetry via API | System story: Subscribe over WebSocket to the organization's live positions, telemetry and incident events. FR-AUTH-11: WHILE an organization member or an organization API key is authenticated, the system SHALL restrict every read and push of devices, positions, telemetry, incidents, contracts and invoices, over REST and WebSocket, to that organization's records, and SHALL enforce this on the server. FR-MON-05: WHEN a WebSocket client reconnects with a last-event cursor, the system SHALL replay the events after it before resuming the live stream, and the web client SHALL show a reconnecting indicator meanwhile. FR-MON-06: WHEN an API client connects with a valid organization key, the system SHALL stream the positions, telemetry and incident events attributed to that organization, and SHALL answer an over-limit client with 429. Business rules: BR-19, BR-20 (SRS section 3.3). Alternatives and exceptions: Key revoked or rate limit exceeded: 401 or 429 (E04-5). Device of another organization: never sent (E04-4). | EP07 | MF-04 | Low | 3 | 4 | Backlog | LongNN | no
Story | US-UC40 | UC-40 Query Device History | As an Org Operator, I want to read a rented device's position and telemetry history for the contract period. FR-AUTH-11: WHILE an organization member or an organization API key is authenticated, the system SHALL restrict every read and push of devices, positions, telemetry, incidents, contracts and invoices, over REST and WebSocket, to that organization's records, and SHALL enforce this on the server. FR-MON-07: The system SHALL serve a device's position and telemetry history over REST only within the periods the caller's organization rented it. Business rules: BR-19 (SRS section 3.3). Alternatives and exceptions: Period outside the contract: only the overlap is returned. | EP07 | MF-04 | Low | 2 | 4 | Backlog | LongNN | no
Story | US-UC41 | UC-41 Mark Stale Device | System story: Flag devices and Field Stations that have been silent beyond their thresholds. FR-INC-13: WHEN a device goes silent during an open incident, the system SHALL keep the incident's state, flag it stale with the last position and notify the owner. FR-MON-03: WHILE a device or Field Station has been silent beyond its configured threshold, the system SHALL display it as stale with its last-seen time. Business rules: BR-21 (SRS section 3.3). No alternative flow in the SRS specification. | EP07 | MF-04 | High | 2 | 4 | Backlog | LongNN | yes
Story | US-UC42 | UC-42 View System Health | As a TrekLink Admin, I want to see ingestion, Field Station connectivity and alert delivery health across the platform. FR-EVT-13: The system SHALL report per Field Station the queue depth for each tier, the last sync time, the retry count of the oldest queued event and its software version against the current release. FR-EVT-18: The system SHALL let an Org Manager download the current Field Station release from the portal with its version shown, and the Field Station SHALL report its version in every health message; WHERE a station runs an older version, the system SHALL show it as outdated to the Manager and to TrekLink Staff. FR-MON-10: The system SHALL show Admins ingestion rate, duplicate and malformed counts, Field Station connectivity and failed alert deliveries. No alternative flow in the SRS specification. | EP07 | MF-04 | High | 2 | 4 | Backlog | LongNN | yes
Story | US-UC59 | UC-59 View Reports | As a TrekLink Admin or TrekLink Staff, I want to fleet utilization, revenue per variant, overdue and lost units, and alert response times. FR-BILL-10: The system SHALL provide utilization, revenue per variant, overdue and lost-unit reports and time-to-acknowledge and time-to-resolve over a date range, exportable as CSV. No alternative flow in the SRS specification. | EP07 | X | High | 2 | 3 | Backlog | LongNN | yes
Epic | EP08 | Billing | Online payment through SePay, counter payments, contract balance with late and damage fees, damage charge approval, loss charges and reports. |  |  |  | 13
Story | US-UC19 | UC-19 Pay Online | As an Org Manager, I want to pay an amount due by VietQR through the payment gateway; the confirming webhook records the payment. FR-BILL-07: WHEN an Org Manager pays online, the system SHALL create a payment at the payment gateway in its sandbox environment with a unique reference, show its VietQR code, and record the payment only from the gateway's confirming webhook. FR-BILL-08: WHEN a payment confirmation or a counter payment carries a reference already recorded, the system SHALL record nothing and log the duplicate. FR-BILL-09: IF a payment fails, THEN the system SHALL keep the amount due and visible to the Org Manager and Staff, and SHALL write no partial settlement. Business rules: BR-31, BR-34 (SRS section 3.3). Alternatives and exceptions: Webhook repeated, or a counter payment already recorded: no-op, logged (E01-6). Payment not confirmed: nothing recorded; the amount stays due, MSG25. | EP08 | MF-01, MF-05 | High | 3 | 3 | Backlog | LongLP | yes
Story | US-UC22 | UC-22 Record Counter Payment | As a TrekLink Staff, I want to record a cash or bank-transfer payment received at the counter, with its reference. FR-BILL-08: WHEN a payment confirmation or a counter payment carries a reference already recorded, the system SHALL record nothing and log the duplicate. Business rules: BR-31 (SRS section 3.3). Alternatives and exceptions: Reference already recorded: MSG10. | EP08 | MF-01, MF-05 | High | 2 | 3 | Backlog | LongLP | yes
Story | US-UC45 | UC-45 Calculate Contract Balance | System story: Compute what the organization owes: term balance plus late, damage and loss charges. FR-BILL-01: The system SHALL price a monthly term as the variant's monthly price times the quantity, with a holding fee of the configured ratio (default one half) due at the term start, retained as part of the fee, and the remainder due at the term end. FR-BILL-06: The system SHALL issue one immutable, itemized invoice per term or day plan and per closing balance, with corrections only as documented adjustments. Business rules: BR-06, BR-23, BR-24, BR-25 (SRS section 3.3). Alternatives and exceptions: A damage charge awaits approval: the invoice waits for UC-48. | EP08 | MF-05 | High | 2 | 5 | Backlog | LongLP | yes
Story | US-UC46 | UC-46 Apply Late Fee | System story: Add a late fee per device per day when devices come back after the grace period. FR-BILL-03: WHEN devices come back after the end plus the grace period, the system SHALL charge a late fee per device per day as its own invoice line. Business rules: BR-23 (SRS section 3.3). No alternative flow in the SRS specification. | EP08 | MF-05 | High | 2 | 5 | Backlog | LongLP | yes
Story | US-UC47 | UC-47 Apply Damage Fee | System story: Add a damage charge from the schedule when an inspection records damage. FR-BILL-04: WHEN an inspection records damage, the system SHALL price it from the damage schedule; IF the charge exceeds the approval threshold, THEN the system SHALL hold it until an Admin other than the inspector approves, reduces or waives it. Business rules: BR-24 (SRS section 3.3). No alternative flow in the SRS specification. | EP08 | MF-05 | High | 2 | 5 | Backlog | LongLP | yes
Story | US-UC48 | UC-48 Approve Damage Charge | As a TrekLink Admin, I want to approve a damage charge above the threshold; the approver is never the inspector. FR-BILL-04: WHEN an inspection records damage, the system SHALL price it from the damage schedule; IF the charge exceeds the approval threshold, THEN the system SHALL hold it until an Admin other than the inspector approves, reduces or waives it. Business rules: BR-24 (SRS section 3.3). Alternatives and exceptions: The approver is the inspector: refused, MSG30 (E05-6). | EP08 | MF-05 | High | 2 | 5 | Backlog | LongLP | yes
Epic | EP09 | Platform configuration and audit | Plans and prices, business parameters from the Configuration Matrix, the audit log and the scheduler. |  |  |  | 6
Story | US-UC56 | UC-56 Configure Plans and Prices | As a TrekLink Admin, I want to set monthly prices per variant, day-plan lengths and premium, minimum order quantity and fee schedules. FR-CFG-01: The system SHALL read every business parameter registered in the Configuration Matrix from configuration, and a change SHALL take effect without a redeploy. FR-CFG-02: WHEN a business parameter or price changes, the system SHALL record the old value, new value, actor and UTC time in an append-only trail, and SHALL apply a price change only to contracts requested after it. Business rules: BR-02, BR-06, BR-07, BR-29 (SRS section 3.3). Alternatives and exceptions: A premium below 1: MSG02. | EP09 | X | High | 2 | 3 | Backlog | Khoa | yes
Story | US-UC57 | UC-57 Configure Business Parameters | As a TrekLink Admin, I want to change thresholds, timeouts and windows at run time, with an audit trail. FR-CFG-01: The system SHALL read every business parameter registered in the Configuration Matrix from configuration, and a change SHALL take effect without a redeploy. FR-CFG-02: WHEN a business parameter or price changes, the system SHALL record the old value, new value, actor and UTC time in an append-only trail, and SHALL apply a price change only to contracts requested after it. FR-CFG-03: The system SHALL hold the map provider, tile URL and default viewport in configuration. Business rules: BR-29 (SRS section 3.3). Alternatives and exceptions: Value out of its allowed range: MSG02. | EP09 | X | High | 2 | 3 | Backlog | Khoa | yes
Story | US-UC58 | UC-58 View Audit Log | As a TrekLink Admin, I want to read the append-only audit logs of accounts, devices, contracts, incidents and configuration. FR-AUTH-08: The system SHALL record every authentication event with actor, event type, IP and UTC time, append-only, and SHALL NOT store an attempted password in any form. FR-DEV-11: The system SHALL present a read-only chronological history per device of contracts, incidents, inspections, maintenance and state changes, each with actor and UTC time. FR-CFG-02: WHEN a business parameter or price changes, the system SHALL record the old value, new value, actor and UTC time in an append-only trail, and SHALL apply a price change only to contracts requested after it. Business rules: BR-18 (SRS section 3.3). No alternative flow in the SRS specification. | EP09 | X | High | 2 | 3 | Backlog | Khoa | yes
Epic | EP10 | Delivery and quality | Local stack, CI, seed data, deployment to Neon, and the separate isolation and load test suite of D-042. |  |  |  | 13
Story | US-X01 | Local stack and CI | Delivery story: Docker Compose for Postgres, Mosquitto and the backend, and GitHub Actions running lint, typecheck, unit tests and build on every PR. The stack SHALL start with one command and pass the health check of `GET /health`. WHEN a PR is opened, CI SHALL run lint, typecheck, unit tests and build, and SHALL block the merge on failure. | EP10 | X | High | 3 | 3 | Backlog | Khoa | no
Story | US-X02 | Seed data and database script | Delivery story: A seed that loads plans, hardware variants, devices, one active organization with members and one contract, for demos and tests; the migration history doubles as the database script of the software package. The seed SHALL be idempotent and SHALL load on an empty database after `prisma migrate deploy`. The seed SHALL contain no real personal data. | EP10 | X | High | 2 | 3 | Backlog | Khoa | no
Story | US-X03 | Deployment to Neon | Delivery story: Shared dev and production databases on Neon (D-010), with migrations applied by the pipeline. WHEN `dev` is updated, the pipeline SHALL apply pending migrations to the shared dev database. Connection strings SHALL come from environment variables only. | EP10 | X | Medium | 3 | 4 | Backlog | Khoa | no
Story | US-X04 | Isolation and load test suite | Delivery story: The separate suite of D-042: multi-organization isolation and ingestion load. The suite SHALL show that no endpoint returns another organization's data. The suite SHALL report ingestion throughput and latency against the SRS non-functional targets. | EP10 | X | Medium | 5 | 5 | Backlog | Khoa | no

## Week 3 baseline
Week 3 UC | Week 3 name | Current use cases | Delivered by stories
UC-01 | Browse Trek Packages | UC-15 | US-UC15
UC-02 | Submit Booking | UC-15 | US-UC15
UC-03 | Reserve Device | UC-16 | US-UC16
UC-04 | Confirm Booking | UC-17 | US-UC17
UC-05 | Allocate Device | UC-20 | US-UC20
UC-06 | Assign Guide | UC-25 | US-UC25
UC-07 | Generate Rental Agreement | UC-21 | US-UC21
UC-08 | Check Out Device | UC-20 | US-UC20
UC-09 | Check In Device | UC-43 | US-UC43
UC-10 | Inspect Returned Device | UC-44 | US-UC44
UC-11 | Calculate Rental Charge | UC-45 | US-UC45
UC-12 | Process Payment | UC-19, UC-22 | US-UC19, US-UC22
UC-13 | Ingest Field Event | UC-26 | US-UC26
UC-14 | View Live Map | UC-38 | US-UC38
UC-15 | Acknowledge Incident | UC-32 | US-UC32
UC-16 | Update Incident Status | UC-33 | US-UC33
UC-17 | Record Response Note | UC-33 | US-UC33
UC-18 | Manage Users and Roles | UC-10, UC-04 | US-UC10, US-UC04
UC-19 | Configure Business Parameters | UC-57 | US-UC57
UC-20 | View Audit Log | UC-58 | US-UC58
UC-21 | Authenticate | UC-08 | US-UC08
UC-22 | Verify Device Availability | UC-16 | US-UC16
UC-23 | Send Notification | UC-30 | US-UC30
UC-24 | Apply Late Fee | UC-46 | US-UC46
UC-25 | Apply Damage Fee | UC-47 | US-UC47
UC-26 | Reopen Incident | UC-36 | US-UC36
UC-27 | Register Account | UC-01 | US-UC01
UC-28 | Reset Password | UC-09 | US-UC09
UC-29 | Cancel Booking | UC-18 | US-UC18
UC-30 | Extend Reservation Hold | removed by D-033
UC-31 | Manage Trek Packages | UC-56 | US-UC56
UC-32 | Create Trip | removed by D-033
UC-33 | Request Trip | removed by D-033
UC-34 | Reschedule Trip | removed by D-033
UC-35 | Start Trip | removed by D-033
UC-36 | End Trip | removed by D-033
UC-37 | Confirm Device Handover | UC-21 | US-UC21
UC-38 | Register Device | UC-11 | US-UC11
UC-39 | Provision Channel Key | UC-14 | US-UC14
UC-40 | Report Missing Device | UC-49 | US-UC49
UC-41 | Record Maintenance | UC-52 | US-UC52
UC-42 | Retire Device | UC-53 | US-UC53
UC-43 | Sign Rental Agreement | UC-21 | US-UC21
UC-44 | Approve Fee Waiver | UC-48 | US-UC48
UC-45 | View Booking History | UC-55 | US-UC55
UC-46 | Dismiss Suspected Incident | UC-34 | US-UC34
UC-47 | Create Manual Incident | UC-29 | US-UC29
UC-48 | Trigger SOS | UC-26 | US-UC26
UC-49 | Create Incident | UC-29 | US-UC29
UC-50 | Manage Pricing Rules | UC-56 | US-UC56
UC-51 | Manage Device Types | UC-13 | US-UC13
UC-52 | View Reports | UC-59 | US-UC59
UC-53 | View System Health | UC-42 | US-UC42
UC-54 | Flush Offline Queue | UC-27 | US-UC27
UC-55 | Expire Reservation Hold | removed by D-033
UC-56 | Mark Stale Device | UC-41 | US-UC41
UC-57 | Escalate Unacknowledged Incident | UC-31 | US-UC31
UC-58 | Escalate Unreturned Device | UC-50 | US-UC50

## Workload
Member | Code | Stories | Points | Secondary stories | Modules
Đỗ Đăng Khoa | KhoaDD | 24 | 72 | 0 | devices, devops, gateway-sync, platform
Lâm Phi Long | LongLP | 20 | 54 | 1 | auth, billing, rentals
Trần Khải Hoàng | HoangTK | 9 | 23 | 6 | incidents
Nguyễn Ngọc Long | LongNN | 7 | 16 | 44 | monitoring, rentals
Nguyễn Bá Tân | TanNB | 9 | 27 | 1 | organizations